## Slide 1: Suicide Prevention Advisory Group
July 25, 2023

## Slide 2
Time | Item | Objective
3:00-3:05 | Agenda | Agenda Review
3:05 – 3:20 | Workplan and Timeline | Review Workplan Updates & Timeline for next few months
3:20 – 3:55 | Engagement/Discussion | Unit Charter Role Charter Executive Committee Membership & Charter
3:55-4:00 | Next Steps | Review opportunities to provide feedback and preview next month’s session topics
Agenda

## Slide 3: Suicide Prevention Workplan
Output | Target Start Date | Target Completion Date | Total Days to Complete | Days Remaining to Complete | Status
Unit Charter | 7/24/2023 | 8/4/2023 | 11 | 10 | In Progress
Role Charter | 7/24/2023 | 8/4/2023 | 11 | 10 | In Progress
Executive Committee Membership & Charter Template | 7/24/2023 | 8/25/2023 | 32 | 25 | In Progress
Purview Statement | 7/18/2023 | 8/25/2023 | 38 | 25 | Not Started
Portfolio Analysis Report | 7/18/2023 | 8/25/2023 | 38 | 25 | Not Started
Position Description/Functional Statement | 8/7/2023 | 9/29/2023 | 53 | 50 | Not Started
Work Group Membership and Charter Template | 7/24/2023 | 9/29/2023 | 67 | 50 | Not Started
Portfolio Analysis Powerpoint | 8/28/2023 | 10/27/2023 | 60 | 70 | Not Started
Critical Research Priorities document | 8/28/2023 | 12/22/2023 | 116 | 110 | Not Started
Funding Model SOP | 8/28/2023 | 10/27/2023 | 60 | 70 | Not Started
Review Calendar | 9/25/2023 | 10/27/2023 | 32 | 70 | Not Started
Review Policy(s) SOP | 9/25/2023 | 10/27/2023 | 32 | 70 | Not Started
Research LOI Guidelines | 10/23/2023 | 11/24/2023 | 32 | 90 | Not Started
Research LOI Template | 10/23/2023 | 11/24/2023 | 32 | 90 | Not Started
Clincial Trials LOI Guidelines | 10/23/2023 | 11/24/2023 | 32 | 90 | Not Started
Clinical Trials LOI Template | 10/23/2023 | 11/24/2023 | 32 | 90 | Not Started
Clinical Trial RFA(s) | 1/1/2024 | 2/2/2024 | 32 | 140 | Not Started
Research RFA(s) | 1/1/2024 | 2/2/2024 | 32 | 140 | Not Started
Portfolio Performance Metrics | 1/1/2024 | 2/2/2024 | 32 | 140 | Not Started

## Slide 4: Suicide Prevention Stand-up Deliverable Timeline
Aug 2023
Sept 2023
Oct 2023
Nov 2023
Dec 2023
Jan 2023
Feb 2023
Unit Charter
Role Charter
Executive Committee Charter
Purview Statement
Portfolio Analysis Report
Position Description
Work Group Charter
Portfolio Analysis PPT
Critical Research Priorities
Research LOI Guidelines
Research LOI Template
Clinical LOI Guidelines
Clinical LOI Template
Clinical Trial RFAs
Research RFAs
Portfolio Performance Metrics
(TBD)
Based on the Suicide Prevention workplan, the team plans to complete the designated documents by the end of these months. The team will share these documents with this advisory for feedback and input while tracking towards this timeline.

## Slide 5: Suicide Prevention AMP – Advisory Group Look-Ahead
July Session (Present)
  Unit Charter
  Role Charter
  Executive Committee Membership & Charter
August Session
  Purview Statement
  Portfolio Analysis Report
September Session
  Position Description / Functional Statement
  Workgroup Membership & Charter