## Slide 1: Suicide Prevention Advisory Group Monthly Meeting
August 22, 2023

## Slide 2
Time | Item | Objective
3:00-3:05 | Agenda | Agenda Review
3:05 – 3:15 | AMP Progress Updates | Review Workplan Updates & Timeline for next few months
3:15 – 3:55 | Engagement/Discussion | Executive Charter Updates Portfolio Analysis Presentation
3:55-4:00 | Next Steps | Review opportunities to provide feedback and preview next month’s session topics
Agenda

## Slide 3: Suicide Prevention AMP – Progress Updates
July Session
  Unit Charter – Completed, Reviewing with ISRM Leadership this week
  Role Charter – Completed, Reviewing with ISRM Leadership this week
August Session (Present)
  Executive Committee Membership and Charter
  Portfolio Analysis Report
September Session
  Purview Statement
  Position Description / Functional Statement
  Workgroup Membership & Charter

## Slide 4
Executive Committee Membership & Charter

## Slide 5
Portfolio Analysis

## Slide 6
Appendix

## Slide 7: Suicide Prevention Stand-up Deliverable Timeline
Aug 2023
Sept 2023
Oct 2023
Nov 2023
Dec 2023
Jan 2023
Feb 2023
Unit Charter
Role Charter
Executive Committee Charter
Purview Statement
Portfolio Analysis Report
Position Description
Work Group Charter
Portfolio Analysis PPT
Critical Research Priorities
Research LOI Guidelines
Research LOI Template
Clinical LOI Guidelines
Clinical LOI Template
Clinical Trial RFAs
Research RFAs
Portfolio Performance Metrics
(TBD)
Based on the Suicide Prevention workplan, the team plans to complete the designated documents by the end of these months. The team will share these documents with this advisory for feedback and input while tracking towards this timeline.