## Slide 1: Suicide Prevention: Advisory Group Monthly Meeting
January 23, 2024
Joe Constans

## Slide 2
Time | Item | Objective
3:00 – 3:05 | Update on AMP activation | Present current state and upcoming tasks Review portfolio purview statement
3:05 – 3:15 | Priority Setting Process and Suicide Prevention AMP Priorities | Review priority setting process Review progress in Suicide Prevention priority development
3:15 – 3:30 | Survey Development | Pain and Opiate Survey Recommendations from Investigators
3:30 – 3:40 | Discussion | Suicide Prevention survey development Survey samples Use of data going forward
3:40 – 3:50 | Next Steps | Review next steps in priority development
Agenda

## Slide 3
Update on Development of a Suicide Prevention AMP

## Slide 4: Portfolio Stand-up Progress
Completed
Future Items
Role Charter
Executive Committee Charter
Portfolio RFAs / Program Announcements
Portfolio Performance Metrics
Purview Statement
Portfolio Analysis Report
Portfolio Analysis PPT
In Progress
Critical Research Priorities
Funding Model SOP
Position Description
Based on the Suicide Prevention workplan, the team plans to complete the designated documents by the end of these months.
November – Mar 2024
Mar - May 2024

## Slide 5
The Suicide Prevention Actively Managed Portfolio (AMP) will include research involving preclinical, translational, clinical, and health services/implementation studies that seek to improve the understanding of suicide and prevent suicidal behavior. Contained within this portfolio will be research using a wide variety of methods and approaches including, but not limited to, studies involving animal models, human tissues and genetic samples, clinical trials of pharmacological and non-pharmacological treatments, application of new technologies, implementation studies (including hybrid studies), observational and epidemiological studies, development of assessment measures, studies concerning risk identification, and studies that seek to understand or address the influence of community on suicidality including investigations on family, caregiver, and peer support, as well as investigations on education, public service announcements, recreation, housing, geospatial location, and employment.
Suicide Prevention Actively Managed Portfolio: PURVIEW STATEMENT

## Slide 6: Last Meeting Recall: Rapid (and Rigorous) Approach to Identifying AMP Research Priorities
AMP Priorities for RFA
Measures of Impact
Exec. Committee
Phase I: Identify research gaps and unanswered questions (e.g., SPM review, evidence inventories or reviews, VA program office strategic plans)
Phase II: Refine Priorities using concurrent processes: national surveys/live voting & focus groups with Consumer, Provider, Leader, Investigator groups
Phase III: Delphi consensus panel with interested party representatives rank priorities on urgency, impact, feasibility, identify impact metrics
Survey and focus group input inform Delphi consensus panel discussion with representatives from different groups
Existing reviews inform focus group, survey questions
References:
Aligning quality improvement efforts and policy goals in a national integrated health system - Braganza - 2022 - Health Services Research - Wiley Online Library;
Health System Research Priorities for Children and Youth With Special Health Care Needs - PubMed (nih.gov),
Research Lifecycle to Increase the Substantial Real-world Im... : Medical Care (lww.com)
General principles:
Priorities should reflect the research translation spectrum (e.g., T1-T4)
In-depth feedback from focus groups to identify topics not previously listed
Broad representation across interested parties via surveys, voting on top priorities
Perspectives from the front line

## Slide 7
Critical Research Priority Development

## Slide 8: Phases to determine Critical Research Priorities
Reviewing existing literature around suicide prevention research priorities
Refining the collected priority list by conducting surveys and discussing priority topics with focus groups. Ranking of topics using structured survey.
Holding a consensus panel with the portfolio’s executive committee to review priorities and rank based on urgency, impact, and feasibility
Braganza, M. Z., Pearson, E., Avila, C. J., Zlowe, D., Øvretveit, J., & Kilbourne, A. M. (2022). Aligning quality improvement efforts and policy goals in a national integrated health system. Health Services Research, 57, 9-19.

## Slide 9: Phase 1: Critical Research Priority Setting for Suicide Prevention
Utilizing these sources as a base, the team gathered priorities from a total of 26 sources, resulting in 186 cumulative priorities
These priorities were coded into research categories to reflect method/procedure and characteristic of prioritized population.
American Foundation for Suicide Prevention
American Psychological Association
CDC
Defense Health Agency (DHA)
Department of Defense
Indian Health Service
National Action Alliance for Suicide Prevention (NAASP)
NAMI
NIMH
SAMSHA
VHA
White House
Peer-reviewed Research

## Slide 10: Phase 1: Developing the Priority Matrix
Category | Cross-Cutting | Firearms | Older Veterans | Younger Veterans (22-34) | Female Veterans | Race/Ethnicity | SDOH | Substance Abuse | Medical Disease | TBI | Justice Involvement | LGBTQ | Trauma/ Moral Injury | Mental Health
Biology/ Genomics/Brain |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Risk Factor Assessment/ Screening - clinician/questionnaire |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Risk Factor Assessment - machine learning |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Continuous monitoring |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Family /Social Network |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pharmacotherapy and other Somatic Interventions |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Psychotherapy and other Non-Somatic Interventions |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Community Interventions |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Education, Training, & Messaging |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Precision Medicine ? |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cross-Cutting |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Postvention |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First Column – Categories reflect Method or Procedure.
First Row – Categories reflect Risk Factors
A priority could be placed into a cell reflecting risk factor and method.

## Slide 11: Phase 2: Gathering input from various stakeholders
Priority Questionnaire Distribution to Field (November 17, 2023)
  A survey was sent out to investigators within the SPRINT database. We collected responses from 54 respondents, each listing ranked research priorities. These priorities were coded into the categories developed in Phase 1.
Veteran’s Engagement Council Discussion (December 7, 2023)
  Our team met with a Veteran’s Engagement Council in December to hold a discussion and gather research topics of interest to veterans.
VISN Suicide Prevention Lead – Open Discussion (January 11, 2024)
  Understanding Research Priorities from the perspective of VISN Leads for Suicide Prevention Coordinators.
Discussion with VA Investigators (January 19, 2024)
  Discussion of qualitative data obtained and solicitations of recommendations for quantitative survey.

## Slide 12: Phase 2: Priority Questionnaire Distribution to Field
Greetings VA Suicide Prevention investigators,
Beginning October 1, 2024, suicide prevention research will be housed within the Suicide Prevention Actively Managed Portfolio (SP AMP). The SP AMP team is currently working with an Executive Steering Committee to establish governance policy and processes for the SP AMP and to establish initial priority areas for VA suicide prevention research.
The priority setting efforts will follow a strategy developed by QUERI which seeks input from multiple stakeholders throughout the priority setting process. As part of our initial efforts, we are asking for your assistance in identifying topic areas that you believe are important to advance suicide prevention efforts in VA. To help us gather a thorough body of topic areas, we ask that you identify up to 10 research areas for which there are significant gaps in extant knowledge and for which research support is needed.
If you are willing to assist us in these initial efforts to identify possible priority areas, please click on this link which will provide further instruction. Please provide feedback as soon as possible but no later than November 17th.
Thanks in advance for your willingness to help. We will be providing more information to the field as this process advances.

## Slide 13: Phase 2: Categorizing Priority Questionnaire Responses
Initial Categorization of Priorities Identified by Survey Respondents
Category | Cross-Cutting | Firearms | Older Veterans | Younger Veterans (22-34) | Female Veterans | Race/Ethnicity | SDOH | Substance Abuse | Medical Disease | TBI | Justice Involvement | LGBTQ | Trauma/ Moral Injury | Mental Health | SUM
Biology/ Genomics/Brain | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
Risk Factor Assessment/ Screening - clinician/questionnaire | 25 | 0 | 5 | 5 | 0 | 0 | 8 | 0 | 10 | 0 | 0 | 0 | 0 | 3 | 56
Risk Factor Assessment - machine learning | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
Continuous monitoring | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Family /Social Network | 13 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
Pharmacotherapy and other Somatic Interventions | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 30
Psychotherapy and other Non-Somatic Interventions | 42 | 25 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 5 | 5 | 1 | 100
Community Interventions | 56 | 7 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68
Education, Training, & Messaging | 17 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
Precision Medicine ? | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Cross-Cutting | 5 | 49 | 34 | 3 | 25 | 16 | 32 | 2 | 4 | 4 | 5 | 31 | 6 | 18 | 
Postvention | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
SUM |  | 97 | 39 | 13 | 25 | 16 | 62 | 2 | 14 | 4 | 5 | 36 | 11 | 23 | 

## Slide 14: Phase 2: Potential Priorities as identified through Matrix coding
Category | Example Responses to Unstructured Survey
Psychotherapy and other Non-Somatic Interventions | Multi-site RTC to determine interventions most likely to prevention suicide death.
Firearms, Lethal Means Safety | Does LMS counseling in primary care settings reduce suicide deaths?
Community Interventions | What community interventions effectively promote safe storage?
Social Determinants of Health | Do programs that address SDOH (i.e., providing housing to unhoused Veterans) decrease suicide for those at risk?
Risk Factor Assessment – Screening | How can algorithms be improved to include dynamic risk factors of suicide?
Biology, Genomics, Brain | Neuroimaging (fMRI, DTI, MRS) studies of suicide: emphasis on measures of impulsivity, negative affect processing, reward, decision making.
Older Veterans | Developing age-specific interventions for older Veterans.
LGBTQ+ | Interventions for sexual minority / LGBQ veterans.

## Slide 15: Phase 2: Veteran’s Engagement Council Discussion
Research Priorities Discussed during Meeting
Key Questions for Audience:
What suicide prevention research topics come to mind as most important for Veterans from your perspective?
Are there specific patient populations it would be important to study (if this has not come up)?
Are there any research topics you don’t think are as high a priority?
Are there particular topics within this area that come to mind that would be important for VA researchers to work on?
Hard to Reach Veterans (Isolating Veterans/ Veterans not in VA care/ Rural Veterans / Transitioning to civilian)
Continuity of Care*
Community Research (including family)
Developing Novel Treatments (including provider perspective)
Moral Injury/Spiritual
Lethal Means Safety
Messaging
Peer Support
Messaging
Data Studies
Racial/Ethnic/Sexual Minorities
Brain/TBI/Genomics (low priority)
* - category not identified through investigator survey

## Slide 16: Phase 2: VISN Suicide Prevention Lead – Open Discussion
Research Priorities Discussed during Meeting
Key Questions for Audience:
What areas in suicide prevention do you think needs more research to support your clinical decision-making?
How does your program implement current research evidence or data regarding assessing suicide risk? What would make risk assessment processes or resulting risk information more useful or actionable?
How do you use the information you have now regarding effectiveness of suicide prevention interventions and treatments? What new information would help your program make evidence-informed treatment planning decisions?
Are there certain patient characteristics that are important to study or to include in VA research?
Risk Identification Process*
  Needs modification
  Clinician burden too high
Clinical Trial Feasibility*
  Psychotherapy
  Small trials will not advance practice
Community Interventions
Education, Training, and Messaging
Firearms, Lethal Means Safety
Safety Planning
Older Veterans
Female Veterans
* - similar category / different perspective

## Slide 17
Survey development for Phase 3

## Slide 18: Phase 3: Pain/Opioid Use AMP Survey
Purpose: The VHA Pain and Opioid actively managed portfolio in the Office of Research and Development is requesting input on research priorities related to pain and opioid use experienced by Veterans.
This survey is part of a larger initiative to obtain input on research priorities from different groups including clinical leaders, researchers, Veterans, and the frontline providers who care for them.
For research priorities related to pain, please consider different types of pain such as neuropathic pain (e.g., due to damages in the nervous system) as well as for musculoskeletal pain (e.g., due to damages to the connective tissues including bones, muscles, etc.).
For research priorities related to opioids, please also consider accidental opioid overdose rescue and the effects of opioid tapering.
For both pain and opioid use, we are interested in your input on research priorities across the scientific translation spectrum:
Basic research (e.g., understanding biological bases for pain and addiction)
Clinical research (e.g., testing new treatments and understanding their mechanisms)
Health systems and policy (e.g., long-term outcomes of treatments, how to implement effective treatments, and understanding how to optimize programs and polices based on socio-economic factors)
Responses will be confidential and aggregated to help inform VHA research funding priorities.

## Slide 19: Phase 3: Pain/Opioid Use AMP Survey
Q.1. The following is a list of currently identified VHA research priorities related to opioid use disorder and pain management. Your feedback on these research priorities will help inform a VA program of research that is focused on improving outcomes for Veterans with opioid or other substance use disorders, as well as those experiencing pain. At the end you also have an opportunity to write in other specific priorities not included in this list.
Please select and rank your top three research priorities. [Priority option order will be randomized]
(X) Clinical studies of the genetic, anatomical, and behavioral bases of pain, tolerance, addiction, opioid metabolism, and tapering of opioid medication
(X) Research on the risk factors, treatment, and prevention of opioid use disorder resulting from fentanyl-based products, prescription painkillers, and heroin products
(X) Preclinical development and translation of non-opioid therapies, including medications, complementary and integrative approaches; and the accompanying anatomical, molecular, biochemical, behavioral, and genetic mechanism(s).
(X) Studies identifying therapeutic targets for pain, tolerance, and/or opioid use disorder in acute and chronic painful conditions.
(X) Experimental and observational interventional to improve outcomes in opioid use disorder, including new models for opioid use disorder and substance use disorder care, medication and behavioral therapy for opioid use disorder, use of overdose rescue medication, and self-help groups.
(X) Examination of pharmacology, pharmacotherapeutics, pharmacogenomics, and phenotypes as well as the use of functional outcomes (e.g., correlating subjective pain measures with objective measures of function such as ADL, gait kinetics and kinematics, range of motion, and Quality of Life or activity measures, etc.).
(X) Clinical treatments for long-term recovery from pain emphasizing non-opioid medications and complementary and integrative approaches. This includes studies that use novel designs including pragmatic trials or cluster randomized trials to maximize study sample size, retention, and enrollment from typical practice or community settings.
(X) Implementation of treatments and approaches across VAMCs, evaluation of methods to enhance pain services, and evaluation of the quality and safety of pain care, especially for underserved and marginalized groups (e.g., people with sickle cell risk).
(X) Environmental and/or policy interventions that address social determinants to prevent opioid misuse and promote effective opioid use disorder treatment retention and recovery over time. Non-comprehensive examples include Veterans benefits programs, policy interventions for at-risk and marginalized groups, or jail diversion programs such as drug courts.
(X) Other priority not listed (please specify priority below)

## Slide 20
Q.2. Other research priority not previously listed– Please Specify
Q.3. If you have any additional comments or ideas regarding the VHA research priorities related to opioid use disorder and pain management, please use the space below.
Q.4. If you have any additional comments regarding the VHA research prioritization process related to opioid use disorder and pain management, please use the space below.
Phase 3: Pain/Opioid Use AMP Survey

## Slide 21: Phase 3: Discussion with Investigators to develop Survey
Suggestions regarding weighting of quantitative and qualitative data to identify content domains for consideration?
Thoughts on ranking or rating of content domains in the survey? That is, what do you see as the benefits of ranking over rating and visa versa?
How many domains should be considered on the survey?
What are the recommendations regarding specificity in the domains in survey?
  For example, if Lethal Means Safety
    Should we leave it at the content domain (Lethal Means Safety)
    Or should we present different options regarding intersection between population and methods (i.e., LMS in primary care; LMS in community)

## Slide 22: Phase 3: Recommendations from Investigators on Survey Format
Survey Content
  Use of count data
  Include themes important to non-investigator stakeholders
Recommended different instructions
  Framing language to define what is meant by “important”
Broad Categories
  Rate categories
  Rank top 3 categories
  Specify what should be studied in top 3 categories
Populations
  Rank each population

## Slide 23
Next Steps

## Slide 24: Next Steps and Discussion
Identification of all recipients for Survey
Distribution of Suicide Prevention Survey
Selection of experts to present priority topics
Consensus Panel Meeting